## Work plan
CAI 8103 Capstone II — Updated work plan (JAN26/MAIDS/0077U), as at 19 Oct 2026
Dates assume a final examination in early December 2026; edit Start/End (blue) if the date differs. Duration is calculated.
# | Activity | Phase | Status | Start | End | Duration (days) | Evidence / output
1 | Data ingestion, cleaning, annual aggregation, GIS integration | Capstone I | Completed |  |  |  | notebooks/uganda_electricity_loss_risk.ipynb
2 | Descriptive analysis, VIF screening, K-Means, LOEO tree models, SHAP, final report and manuscript draft | Capstone I | Completed |  |  |  | Capstone I report; manuscript draft
3 | Leakage audit; leakage-safe lag features (loss_lag1, loss_slope_lag3) | Capstone II | Completed | 2026-10-01 | 2026-10-19 | 19 | capstone2/build_panel.py, leakage_audit.py, tables/leakage_audit.csv
4 | Clipped transmission, GIS imputation flag, coverage audit, full-boundary map | Capstone II | Completed | 2026-10-01 | 2026-10-19 | 19 | capstone2/gis_features.py, figures/c2_archetype_map.png
5 | Structural/Persistence/Forecast x Ridge/RF/XGBoost; mean and naive-persistence baselines; bootstrap CIs; ablation; complete-case check | Capstone II | Completed | 2026-10-01 | 2026-10-19 | 19 | capstone2/models.py, tables/loeo_results_main.csv
6 | Rolling-origin validation; entity-level archetypes with bootstrap ARI; out-of-fold SHAP | Capstone II | Completed | 2026-10-01 | 2026-10-19 | 19 | tables/rolling_origin_metrics.csv, cluster_bootstrap_ari.csv, oof_attribution_*.csv
7 | Modular pipeline, runner, 6 automated tests, Git branch capstone2 | Capstone II | Completed | 2026-10-01 | 2026-10-19 | 19 | capstone2/run_all.py, tests/test_pipeline.py
8 | Ingest ERA Q4 2025 statistics; prospective test (train <=2022, test 2023-2025); flag Umeme handover (31 Mar 2025) | Capstone II | Outstanding | 2026-10-20 | 2026-11-02 | 14
9 | Model change from persistence (delta-loss target); report skill relative to naive persistence | Capstone II | Outstanding | 2026-10-27 | 2026-11-09 | 14
10 | Conformal prediction intervals for licensee-level screening | Capstone II | Outstanding | 2026-11-03 | 2026-11-09 | 7
11 | Shock analysis 2018-2020 (BECS, NWST); sensitivity excluding GIS-imputed licensees | Capstone II | Outstanding | 2026-11-03 | 2026-11-16 | 14
12 | Peer-benchmarking screening prototype (archetype z-scores, persistence flags, intervals) | Capstone II | Outstanding | 2026-11-10 | 2026-11-23 | 14
13 | Revise manuscript with clean results; final report; demonstration rehearsal | Capstone II | Outstanding | 2026-11-17 | 2026-11-30 | 14
| Completed activities | 7
| Outstanding activities | 6
| Share completed | 53.85%